Dublin City Public Participation Network (PPN)

2025 Workplan Q2 Report

April - June 2025

This 2025 draft workplan and budget for Dublin City PPN is informed by several documents: the Dublin City PPN’s own Five-Year Strategic Plan (2022), and previous annual workplans; the PPN Handbook (2020). and the PPN Implementation RoadMap (July 2024), which can be accessed on the PPN website here.

The 2025 draft workplan is ratified at the November Plenary and implemented by PPN staff, Secretariat, Representatives and other stakeholders.

|  | Objective One: Optimising the PPN Network Goals: Through the continued development of Dublin PPN, facilitate the effective participation and representation of the members of DCPPN in policy and decision-making fora. Consolidate and strengthen the membership base of Dublin City PPN and continue the development of DCPPN as a networking and information hub for member organisations. Optimise the effectiveness of training, networking, and information hub functions through the development of a targeted and concise Communications Strategy and Action Plan |  |  |  |
| --- | --- | --- | --- | --- |
|  | Action | Responsibility | Targets | Key Performance Indicators |
| 1.1 | An Equity/Diversity and Inclusivity (EDI) group to be established. The Disability Thematic Group will continue to meet and organise events. The Migrant Thematic Group (MTG) will meet continue to meet and organise events. Three linkage groups will be established to support the newly elected and re-elected PPN Representatives. | Support Worker and Coordinator No direct staff involvement in this group. The Co-ordinator will continue to support this group (with assistance from the Support Worker). Coordinator, Support Worker and Secretariat | The Support Worker and Coordinator will continue to work with EDI academics from CER/DCU and Dr Ebun Joseph, to establish a PPN EDI group, which will feed into three linkage groups established under the PPN Pillars of community and voluntary/social inclusion and environment. The DTG will continue to meet for monthly meetings, in order to share knowledge and experience about the sector. The MTG will continue to meet for quarterly meetings and will organise events to showcase work. Members of the Secretariat will work with linkage groups, to support the Representatives in their work with the SPCs. | EDI work continued in Q2, in the form of an in-person session at the PPN/DCU Summer School, entitled, “How to recognise and navigate disinformation” with Dr Eileen Culloty. DCU will continue to support this work in Q3/4 with focus group discussions, training in partnership with the libraries, and a written report. The DTG coordinated a meeting on 20 May, (ahead of Inclusion and Integration Week) called, “Building a movement: disability rights and DPOs at the heart of Dublin inclusion” and a summary of the event is here. The DTG meet online, on the first Monday of every month, and plans for Q3 include further DPO work and an event to mark, Make Way Day. The MTG were very active in Q2, and coordinated an event on Sunday 04 May, to celebrate Latvian Independence day, and to mark the work of the other migrant/minority member groups involved in this internal, thematic group. A summary of the event is here. The MTG were also involved in two other events, which are included further on in this report. Time was used during the Plenary in May for the three pillar working groups, to come together and share information. Two out of three pillar working groups are communicating using WhatsApp channels to support one another and get to know one another, and one group is using email. It is clear that the pillar working groups, need additional support from staff and external assistance, to grow and thrive. |
| 1.2 | Continue to improve the quality of online communications via the website: www.dublincityppn.ie | Neo-Archaic, Coordinator and Support Worker. Coordinator Coordinator, Support Worker, Neo-Archaic and SPC Representatives | Neo-Archaic and PPN staff to continue to manage and maintain the website in 2025. The weekly PPN Bulletin will be posted in the news section of the website. An area of the website to be developed to make communications between Representatives and the wider PPN easier and more streamlined. A better “flow” of policy information from the SPC Representatives to the wider PPN to be captured on the PPN website. | Neo-Archaic supported the PPN staff with constant management of the site, and updates as requested. A PPN bulletin is updated to the site every Wednesday at 1.00pm, and Neo-Archaic manage the backend of the site, extremely well. The pillar working groups pages of the website were updated with reports from the working group meetings at the May plenary. |
| 1.3 | The PPN is to review and update its current communications plan. The Support Worker to lead out on planning and implementing a more cohesive communication programme. | Support Worker and Coordinator. | Increase the quality of social media interaction with member groups and develop a calendar of content for staff to follow. A PPN presence on LinkedIn to be established, to support PPN representatives and further discussion of the PPN’s presence on X to be continued. | The communications aspect of the PPN works very well: staff communicate with Secretariat, reps, and the wider PPN through LinkedIn/Facebook/email and WhatsApp. A quarterly newsletter for the Representatives and Secretariat, called “PPN Pulse” was not developed or sent out in Q2. However regular communication through WhatsApp/telephone conversations/emails and social media, continued as this works well. The LinkedIn page continued to show engagement and increased follower numbers and the support worker continues to develop this. It has been a useful tool for reaching PPN members, and PPN Representatives, and for PPN Representatives, who do not use Facebook. |
| 1.4 | Manage the PPN database, Salesforce | Support Worker | Manage new members registrations, review and improve data in Salesforce and welcome new members. | No action required on re-registration in Q2. 3 welcome meetings took place in Q2, which are held on the last Tuesday of the month and are improving in quality each session. The 60-minute online sessions, take the new members through a presentation and the website as a method of explaining the main aims of the PPN, and the activities and where people can find information. This has also been an excellent method for new members to engage with one another. Membership of the PPN remains a criterion for applying for DCC grants in Q2. The PPN has requested its removal, however, DCC are keen for it to remain as criteria. |
| 1.5 | The PPN will continue to have a presence on local community media. | Coordinator, Support Worker, Secretariat & Representatives. | Increase awareness of the PPNs through local community media. | There were no PPN specific radio interviews in Q2, however, many member groups have excellent relationships with local radio, and in particular, NearFM. |
| Objective Two: Organisational Development and Capacity Building Goal: Through the provision of targeted training programmes and networking opportunities, build the capacity of member organisations to improve their effectiveness, and to contribute to and participate in local democratic structures. Develop strategic relationships with key actors in the not-for-profit sector across Dublin City to further the goals of the PPN, and overall sector. |  |  |  |  |
| Action |  | Responsibility | Targets | Key Performance Indicators |
| 2.1 | Training for new Representatives and Secretariat An advisory committee to assist the current Representatives and Secretariat with their roles and functions on DCC committees. | Coordinator and Support Worker and consultant facilitator. “Retired” Secretariat and Representatives | New Representatives, Secretariat An advisory committee to meet on request to aid the Secretariat and staff. No formal decision-making powers, but able to offer advice/recommendations. | There were no specific training and support sessions for Representatives and Secretariat in Q2. However, informal support takes place through emails, telephone calls/WhatsApp messages and in-person meetings at PPN events. The new advisory committee did not meet in person or online in Q2. However, all members are connected on one or more of the WhatsApp channels, and are available for mentoring of new Representatives. |
| 2.2 | Training and resources for the wider PPN | Coordinator and Support Worker. Coordinator and Support Worker. Support Worker and Coordinator. | The PPN and the Centre for Engaged Research (CER) at Dublin City University (DCU) will develop a PPN Summer School in 2025. The PPN will signpost training opportunities, and other supports, from already established training organisations, such as the Dublin City Volunteer Centre. The PPN will survey PPN member groups for training needs in early 2025. Member groups will be tracked during the year, which will lead to a report on participation levels within the PPN. Skills based online supports may be offered to PPN member groups (in partnership with DLR and Fingal PPNs), and further work on EDI and/or wellbeing may be considered if requested in the survey. | The PPN Summer School was held in DCU from Monday 26 – Thursday 29 May. This was the fourth, and most interesting and inspiring Summer School, and you can read a full summary of the week here. Every year Summer School increases in quality and collaboration between the Dublin PPNs, and colleagues in DCU. The weekly Bulletin promoted the work of Dublin City Volunteer Centre. The Bulletin is sent via email to the full membership of the PPN, and then uploaded to the website. The website page is linked to the social media channels of Facebook and LinkedIn. The training needs survey was used to curate the training sessions at Summer School, and it will be used to track the members’ groups, and to further inform the autumn season of training sessions, from September onwards. |
| Objective Three: Governance, Administration and Operating Procedures Goals: to support and empower Dublin City PPN to deliver upon its vision of being an effective and inspirational community representative network, through the establishment of robust operating procedures and demonstration of sectoral best practice. |  |  |  |  |
| Action |  | Responsibility | Targets | Key Performance Indicators |
| 3.1 | Fill any vacant seats in 2025 | Coordinator, Support Worker, and Neo-Archaic | There are no planned vacancies in 2025. | There were no vacant seats, nominations or elections in Q2. |
| 3.2 | Coordinate plenaries in May 2025 and November 2025 | Coordinator and Support Worker | Hybrid plenaries will take place towards the end of May and November (depending on bank holidays). | The Plenary took place on Thursday 22 May in the Mansion House, and a summary, “A night of participation, progress and possibility: plenary highlights from the Mansion House” of the event is online here. The summary was shared in the weekly Bulletin, on the social media channels of Facebook and LinkedIn, and uploaded onto the website. The professional photographs taken were shared via email, with all participants, and the excellent evaluation of the night, suggested that there was a great need for the pillar working groups to meet, during Plenary meetings. |
| 3.3 | Attend PPN regional meetings | Coordinator, Support Worker and Secretariat | To meet colleagues in Dun Laoghaire Rathdown and Fingal PPN for support, skills sharing and planning. | PPN staff from 4 Dublin PPNs met during the summer school activities, and it was agreed that staff from DLR and Dublin City would assist one another, during their autumn plenaries. |
| 3.4 | The Secretariat of the PPN to meet to administer the work of the PPN | Coordinator and Support Worker | The Secretariat to meet monthly to discuss the ongoing work of the PPN, to govern, guide and discuss issues as they arise. | The Secretariat met on the second Tuesday of April, May and June, and then takes a summer break until September. This summer break allows the volunteer Secretariat to tend to other commitments, enjoy the good weather, and relax before the business of the autumn season. |
| 3.5 | Documents required for the Department of Rural and Community Development | Coordinator, and Secretariat. Cordinator and Secretariat Coordinator, Support Worker and Secretariat | The 2024 Income and Expenditure Report to be completed by March 2025. The 2024 Annual Report to be completed by June 2025. The 2026 workplan and budget to be shared with the Plenary by November 2025. The PPN, the host (DCVC) and DCC should meet to discuss work, activities and ongoing budget reviews in 2025, once a quarter. The PPN policies and procedures documents to be reviewed and updated before the May 2025 plenary. The Implementation Roadmap (July 2024) document to be used as a guide to ensure policies and procedures are in line with good governance. The PPN Five Year Strategic Plan is to be reviewed and a new one developed. | The Income and Expenditure Report was completed in March 2025, Q1. The annual report is due to be completed in Q3. Shauna McIntyre of DCC, Mike Randall of DCVC and Ruth Powell of the PPN met on 24 April to discuss cross promotional work, the 2026 SLA, and other matters arising. Secretariat members, Kelley and Frank created a sub-group to review and edit the PPN policies, procedures and constitution. This is an ongoing project, which should be finalised by the November plenary. There were no updates on this in Q2. There were no updates in this area in Q2. There were no updates in this area in Q2. The new 5 Year Strategic Plan will be developed in 2026, after a tender process. |
| 3.6 | Dublin City PPN to relate to national network frameworks and structures. | Coordinator and Support Worker and Secretariat. | Staff to meet PPN staff regionally and nationally, while one member of the PPN Secretariat to belong to the National Secretariat network and feedback to the Dublin City PPN secretariat. | PPN staff meet online every quarter and provide an ongoing support and Q&A area on WhatsApp. Mick Keegan is the Dublin City PPN representative on the National Secretariat Networking meeting. The continuation of the Housing SPC national network is unknown (to be updated by Mike Allen). |
| 3.7 | Maximise virtual technology to support the PPN as requested by Dublin City Council. Assist Dublin City Council staff as it organises events, consultations and information sessions. | All PPN stakeholders All PPN stakeholders | PPN members are better able to use technology to conduct PPN business. PPN to assist DCC’s launch of the LECP. PPN to share information about DCC’s work in the weekly Bulletin and through social media. PPN to attend Africa Day and host events to celebrate Inclusion and Integration Week. PPN to promote training sessions in libraries and at other venues. | PPN staff currently use: telephone/email/whatsapp/teams/zoom/Monday.com/sharepoint/salesforce/Slack/Facebook/LinkedIn and meets members in person. Most member groups prefer face-to-face meetings and staff aim to go on site visits every second week, to support member groups in their activities. Members almost unanimously prefer telephone conversations to any other form of contact. The PPN was active during Inclusion and Integration Week. The DTG held its own event to mark the importance of DPOs, and the PPN staff attended the launch of Inclusion and Integration Week in Wood Quay. The Bulletin includes information from DCC, when requested. The Migrant Thematic Group, also staffed a stand at Africa Day, and a summary of that event can be found here. The PPN Migrant Thematic Group organised an event as part of Dublin Learning City in Q2, and a summary was shared here. PPN member groups attend events at the Dublin City Libraries, and share the information with its groups, when requested. |