Dublin City Public Participation Network (PPN)

2025 Workplan Q3 Report

July - September 2025

This 2025 draft workplan and budget for Dublin City PPN is informed by several documents: the Dublin City PPN’s own Five-Year Strategic Plan (2022), and previous annual workplans; the PPN Handbook (2020). and the PPN Implementation RoadMap (July 2024), which can be accessed on the PPN website here.

The 2025 draft workplan is ratified at the November Plenary and implemented by PPN staff, Secretariat, Representatives and other stakeholders.

|  | Objective One: Optimising the PPN Network Goals: Through the continued development of Dublin PPN, facilitate the effective participation and representation of the members of DCPPN in policy and decision-making fora. Consolidate and strengthen the membership base of Dublin City PPN and continue the development of DCPPN as a networking and information hub for member organisations. Optimise the effectiveness of training, networking, and information hub functions through the development of a targeted and concise Communications Strategy and Action Plan |  |  |  |
| --- | --- | --- | --- | --- |
|  | Action | Responsibility | Targets | Key Performance Indicators |
| 1.1 | An Equity/Diversity and Inclusivity (EDI) group to be established. The Disability Thematic Group will continue to meet and organise events. The Migrant Thematic Group (MTG) will meet continue to meet and organise events. Three linkage groups will be established to support the newly elected and re-elected PPN Representatives. | Support Worker and Coordinator No direct staff involvement in this group. The Co-ordinator will continue to support this group (with assistance from the Support Worker). Coordinator, Support Worker and Secretariat | The Support Worker and Coordinator will continue to work with EDI academics from CER/DCU and Dr Ebun Joseph, to establish a PPN EDI group, which will feed into three linkage groups established under the PPN Pillars of community and voluntary/social inclusion and environment. The DTG will continue to meet for monthly meetings, in order to share knowledge and experience about the sector. The MTG will continue to meet for quarterly meetings and will organise events to showcase work. Members of the Secretariat will work with linkage groups, to support the Representatives in their work with the SPCs. | DCU continues to offer support to the PPN in this area. In Q3 plans took place for a Focus Group Discussion, further training and a report on dis/misinformation. A focus group discussion will take place in Q4. The DTG met online on the first Monday of the month in Q3, and made plans for a follow-up DPO information session, and an event to mark, Make Way Day. These activities are in collaboration with the Independent Living Movement of Ireland (ILMI). The MTG attended the first meeting of the Local Authority Integration Team (LAIT)’s inaugural Community Integration Forum (CIF) on 15 September and the summary of the event is here. The group communicates regularly through its WhatsApp group. Ellenora Lynch was tasked with follow up support work, for the Pillar Working Groups, which she began in February 2025. She plans on delivering 3 x support sessions for each pillar working group and the Local Community Development Committee (LCDC) (as requested). The LCDC representatives delivered a powerpoint presentation to the LCDC on 25 September, which was received very well. |
| 1.2 | Continue to improve the quality of online communications via the website: www.dublincityppn.ie | Neo-Archaic, Coordinator and Support Worker. Coordinator Coordinator, Support Worker, Neo-Archaic and SPC Representatives | Neo-Archaic and PPN staff to continue to manage and maintain the website in 2025. The weekly PPN Bulletin will be posted in the news section of the website. An area of the website to be developed to make communications between Representatives and the wider PPN easier and more streamlined. A better “flow” of policy information from the SPC Representatives to the wider PPN to be captured on the PPN website. | Neo-Archaic supports the PPN Staff on request. In Q3 they were asked to assist with nominations and election materials, as one Representative and one member of the Secretariat stepped down. The Bulletins are postponed during July and August, to give member group some time away from PPN work. PPN staff will continue to develop the “Meet the Reps” section of the website, in Q4. |
| 1.3 | The PPN is to review and update its current communications plan. The Support Worker to lead out on planning and implementing a more cohesive communication programme. | Support Worker and Coordinator. | Increase the quality of social media interaction with member groups and develop a calendar of content for staff to follow. A PPN presence on LinkedIn to be established, to support PPN representatives and further discussion of the PPN’s presence on X to be continued. | Social media outputs continued during Q2. There are daily posts on Facebook and LinkedIn, and the PPN staff also try and attend one live event every second week. A quarterly newsletter for the Representatives and Secretariat, called “PPN Pulse” was not developed or sent out in Q3. Engagement on LinkedIn continued in Q3 and follower numbers continues to grow. |
| 1.4 | Manage the PPN database, Salesforce | Support Worker | Manage new members registrations, review and improve data in Salesforce and welcome new members. | Due to updates from CommIT (who support the Salesforce database), re-registration is not likely until Q3 or Q4. However, the Support Worker is preparing for this by ensuring the database has active up to date contact information before re-registration takes place. New features have been added to salesforce to help the staff manage data more efficiently. The new member meet-up sessions on the last Tuesday of the month, do not take place in July or August, to give new members a quieter time over the summer months. They began again on the last Tuesday of September. They are one-hour, online information sessions, where the PPN staff introduce the aims and objectives of the PPN, and explain the support available. Membership of the PPN remains a criterion for applying for DCC grants in Q3, and the PPN has requested for its removal, however, DCC are very keen for it to remain as criteria. |
| 1.5 | The PPN will continue to have a presence on local community media. | Coordinator, Support Worker, Secretariat & Representatives. | Increase awareness of the PPNs through local community media. | The PPN Coordinator spoke to John Connell from NearFM, on 12 July and you can listen back here. |
| Objective Two: Organisational Development and Capacity Building Goal: Through the provision of targeted training programmes and networking opportunities, build the capacity of member organisations to improve their effectiveness, and to contribute to and participate in local democratic structures. Develop strategic relationships with key actors in the not-for-profit sector across Dublin City to further the goals of the PPN, and overall sector. |  |  |  |  |
| Action |  | Responsibility | Targets | Key Performance Indicators |
| 2.1 | Training for new Representatives and Secretariat An advisory committee to assist the current Representatives and Secretariat with their roles and functions on DCC committees. | Coordinator and Support Worker and consultant facilitator. “Retired” Secretariat and Representatives | New Representatives, Secretariat An advisory committee to meet on request to aid the Secretariat and staff. No formal decision-making powers, but able to offer advice/recommendations. | Ellenora Lynch, begins the second phase of her support work for Representatives and Secretariat in Q3. These sessions include 3 x support sessions for each pillar working group and for the LCDC Representatives. The Secretariat suggested that all training sessions should go out for tender in January 2026, and this was noted in the minutes of the September Secretariat meeting. The new advisory committee did not meet in person or online in Q3. However, all members are connected on one or more of the WhatsApp channels. |
| 2.2 | Training and resources for the wider PPN | Coordinator and Support Worker. Coordinator and Support Worker. Support Worker and Coordinator. | The PPN and the Centre for Engaged Research (CER) at Dublin City University (DCU) will develop a PPN Summer School in 2025. The PPN will signpost training opportunities, and other supports, from already established training organisations, such as the Dublin City Volunteer Centre. The PPN will survey PPN member groups for training needs in early 2025. Member groups will be tracked during the year, which will lead to a report on participation levels within the PPN. Skills based online supports may be offered to PPN member groups (in partnership with DLR and Fingal PPNs), and further work on EDI and/or wellbeing may be considered if requested in the survey. | The PPN engaged with DCU during the summer months, to agree times and dates for a misinformation/disinformation focus group discussion. The weekly Bulletin promoted the work of the Dublin City Volunteer Centre on social media, through the Bulletin and on the website in Q3. During Q2 the PPN staff developed the Autumn series of trainings. The training needs survey was used to inform this. A full list of events can be accessed here. The events are promoted in the Bulletin, and on the online channels of Facebook and LinkedIn and member groups are invited personally (through WhatsApp, email and telephone conversations). |
| Objective Three: Governance, Administration and Operating Procedures Goals: to support and empower Dublin City PPN to deliver upon its vision of being an effective and inspirational community representative network, through the establishment of robust operating procedures and demonstration of sectoral best practice. |  |  |  |  |
| Action |  | Responsibility | Targets | Key Performance Indicators |
| 3.1 | Fill any vacant seats in 2025 | Coordinator, Support Worker, and Neo-Archaic | There are no planned vacancies in 2025. | Two vacancies have become available in Q3: One Secretariat seat and one seat on the Mobility and Public Realm SPC, both from the Community and Voluntary pillar. Both seats were advertised through the website/Bulletin and social media. |
| 3.2 | Coordinate plenaries in May 2025 and November 2025 | Coordinator and Support Worker | Hybrid plenaries will take place towards the end of May and November (depending on bank holidays). | The next Plenary will take place on Thursday 20 November in the rooms of Friends of the Elderly, on Bolton Street. This plenary will allow time for the 2026 workplan and budget to be presented. The plenary will also offer space for the pillar working groups to meet in person, and give time for networking. |
| 3.3 | Attend PPN regional meetings | Coordinator, Support Worker and Secretariat | To meet colleagues in Dun Laoghaire Rathdown and Fingal PPN for support, skills sharing and planning. | PPN staff from 2 Dublin PPNs for a working lunch and networking session in September 2025. These regional meetings provide staff support and networking opportunities. Dublin City PPN staff are putting together a team to attend the PPN National Conference in Meath in October. |
| 3.4 | The Secretariat of the PPN to meet to administer the work of the PPN | Coordinator and Support Worker | The Secretariat to meet monthly to discuss the ongoing work of the PPN, to govern, guide and discuss issues as they arise. | The Secretariat returned to their online meetings on the second Tuesday of September and minutes from Secretariat meetings can be found on the website here. |
| 3.5 | Documents required for the Department of Rural and Community Development | Coordinator, and Secretariat. Cordinator and Secretariat Coordinator, Support Worker and Secretariat | The 2024 Income and Expenditure Report to be completed by March 2025. The 2024 Annual Report to be completed by June 2025. The 2026 workplan and budget to be shared with the Plenary by November 2025. The PPN, the host (DCVC) and DCC should meet to discuss work, activities and ongoing budget reviews in 2025, once a quarter. The PPN policies and procedures documents to be reviewed and updated before the May 2025 plenary. The Implementation Roadmap (July 2024) document to be used as a guide to ensure policies and procedures are in line with good governance. The PPN Five Year Strategic Plan is to be reviewed and a new one developed. | The Income and Expenditure Report was submitted in Q1. Dublin City PPN submitted its annual report on 04 July. The report was co-signed by the PPN staff, the Secretariat and DCC, and submitted to Social Justice Ireland, who will collate all 31 PPN annual reports and deliver a national report by December 2025. There were no 3-way meetings in Q3, however, all three stakeholders communicate regularly via email/telephone conversations and face-to-face meetings. PPN staff attend the bi-weekly DCVC staff meetings. Secretariat members, Kelley, Frank and Catherine will review and edit the PPN policies, procedures and constitution. This is an ongoing project, which should be finalised by the November plenary. There were no updates in this area in Q3. There were no updates due in Q3. A tender for work on the next 5 Year Plan will take place in January 2026. |
| 3.6 | Dublin City PPN to relate to national network frameworks and structures. | Coordinator and Support Worker and Secretariat. | Staff to meet PPN staff regionally and nationally, while one member of the PPN Secretariat to belong to the National Secretariat network and feedback to the Dublin City PPN secretariat. | All 31 PPNs’ staff meet online every quarter and provide daily/weekly support to one another on WhatsApp. Mick Keegan is the Dublin City PPN representative on the National Secretariat Networking meeting. The continuation of the Housing SPC national network is unknown (to be updated by Mike Allen). |
| 3.7 | Maximise virtual technology to support the PPN as requested by Dublin City Council. Assist Dublin City Council staff as it organises events, consultations and information sessions. | All PPN stakeholders All PPN stakeholders | PPN members are better able to use technology to conduct PPN business. PPN to assist DCC’s launch of the LECP. PPN to share information about DCC’s work in the weekly Bulletin and through social media. PPN to attend Africa Day and host events to celebrate Inclusion and Integration Week. PPN to promote training sessions in libraries and at other venues. | PPN staff currently use: telephone/email/whatsapp/teams/zoom/Monday.com/sharepoint/salesforce/Slack/Basecamp/Facebook/LinkedIn and meets members in person. Most member groups prefer face-to-face meetings and staff aim to go on site visits every second week, to support member groups in their activities. The PPN were requested to work closer with DCC area offices, with organisations involving older people, and to provide additional supports to the LCDC. These additional requests were actioned in Q3. The ongoing mis/disinformation will take place in libraries in Q4, and discussions between area offices and the PPN continue (especially Finglas/Ballymun Whitehall/Clontarf and the D8/Liberites area of Dublin City, where PPN staff have made contact with the area managers. A mapping exercise is taking place, to match area offices, with the PPN Representatives, and this will conclude in Q4. |