Dublin City Public Participation Network (PPN)

2025 Workplan Q4 Report

October - December 2025

This 2025 draft workplan and budget for Dublin City PPN is informed by several documents: the Dublin City PPN’s own Five-Year Strategic Plan (2022), and previous annual workplans; the PPN Handbook (2020). and the PPN Implementation RoadMap (July 2024), which can be accessed on the PPN website here.

The 2025 draft workplan is ratified at the November Plenary and implemented by PPN staff, Secretariat, Representatives and other stakeholders.

|  | Objective One: Optimising the PPN Network Goals: Through the continued development of Dublin PPN, facilitate the effective participation and representation of the members of DCPPN in policy and decision-making fora. Consolidate and strengthen the membership base of Dublin City PPN and continue the development of DCPPN as a networking and information hub for member organisations. Optimise the effectiveness of training, networking, and information hub functions through the development of a targeted and concise Communications Strategy and Action Plan |  |  |  |
| --- | --- | --- | --- | --- |
|  | Action | Responsibility | Targets | Key Performance Indicators |
| 1.1 | An Equity/Diversity and Inclusivity (EDI) group to be established. The Disability Thematic Group will continue to meet and organise events. The Migrant Thematic Group (MTG) will meet continue to meet and organise events. Three linkage groups will be established to support the newly elected and re-elected PPN Representatives. | Support Worker and Coordinator No direct staff involvement in this group. The Co-ordinator will continue to support this group (with assistance from the Support Worker). Coordinator, Support Worker and Secretariat | The Support Worker and Coordinator will continue to work with EDI academics from CER/DCU and Dr Ebun Joseph, to establish a PPN EDI group, which will feed into three linkage groups established under the PPN Pillars of community and voluntary/social inclusion and environment. The DTG will continue to meet for monthly meetings, in order to share knowledge and experience about the sector. The MTG will continue to meet for quarterly meetings and will organise events to showcase work. Members of the Secretariat will work with linkage groups, to support the Representatives in their work with the SPCs. | The EDI work continues to flow through the Disability Thematic Group (DTG) and the Migrant Thematic Group (MTG), and both groups will continue into 2026. A separate EDI group will not form into 2026, however, the EDI work will be split between the two thematic groups. The DTG meet online, on the first Monday of every month. These monthly meetings take place to organise activities such as “Make Way Day”. The DTG has also partnered with the Indepenent Living Movement of Ireland, to launch a Dublin City Disabled Persons’ Organisation (DPO), which, once launched will be an ordinary member of the PPN, with its own PPN number. The launch of this DPO will be arranged at the Mansion House for February 2026. The MTG attended a second Local Authority Integration Team (LAIT), meeting in November 2025 and a summary of that meeting is on the website here. The MTG also celebrated Human Rights Day on 10 December, with the LAIT at Wood Quay, which was shared on Facebook and LinkedIn on the channel, @dublincityppn Ellenora Lynch was tasked with supporting the Pillar Working Groups in the autumn of 2025, and worked closely with the Voluntary and Community Pillar Working Group, and the Environment Pillar Working Group. A request from the Chair of the LCDC, also took some attention from the social inclusion pillar working group, towards the Local Community Development Committee (LCDC) (on which the PPN has five representatives). A report of this work will be sent to the Secretariat by the end of Q1 of 2026. |
| 1.2 | Continue to improve the quality of online communications via the website: www.dublincityppn.ie | Neo-Archaic, Coordinator and Support Worker. Coordinator Coordinator, Support Worker, Neo-Archaic and SPC Representatives | Neo-Archaic and PPN staff to continue to manage and maintain the website in 2025. The weekly PPN Bulletin will be posted in the news section of the website. An area of the website to be developed to make communications between Representatives and the wider PPN easier and more streamlined. A better “flow” of policy information from the SPC Representatives to the wider PPN to be captured on the PPN website. | Neo-Archaic supports the PPN Staff, to ensure that the PPN website is functioning correctly and updated. The weekly Bulletins are sent to all members via email, uploaded to the website and shared on the social media platforms of Facebook and LinkedIn. The PPN staff are in constant contact with the website team, Neo-Archaic to improve the user experience of the website. More detailed work will continue the user experience of the website in 2026. |
| 1.3 | The PPN is to review and update its current communications plan. The Support Worker to lead out on planning and implementing a more cohesive communication programme. | Support Worker and Coordinator. | Increase the quality of social media interaction with member groups and develop a calendar of content for staff to follow. A PPN presence on LinkedIn to be established, to support PPN representatives and further discussion of the PPN’s presence on X to be continued. | The PPN posts daily updates on Facebook and LinkedIn. The posts are a variety of updates from member groups, Representatives, Secretariat, other PPNs, the city council and the DRCDG. A quarterly newsletter for the Representatives and Secretariat, called “PPN Pulse” was not developed or sent out in Q4. However, many Representatives contact PPN staff via Whatsapp, the telephone and email. Engagement on LinkedIn continued in Q4 and follower numbers continues to grow. |
| 1.4 | Manage the PPN database, Salesforce | Support Worker | Manage new members registrations, review and improve data in Salesforce and welcome new members. | Re-registration will take place in Q1 of 2026. The Support Worker updates the database daily, and ensures the data is as strong as possible. The November Plenary ratified two changes to operations in November 2025: that the PPN may delete applications of more than 6 months old, and has the right to refuse an application, if the values of the member group, are not in keeping with the values of the PPN. |
| 1.5 | The PPN will continue to have a presence on local community media. | Coordinator, Support Worker, Secretariat & Representatives. | Increase awareness of the PPNs through local community media. | There were no community radio pieces in Q4 of 2026. |
| Objective Two: Organisational Development and Capacity Building Goal: Through the provision of targeted training programmes and networking opportunities, build the capacity of member organisations to improve their effectiveness, and to contribute to and participate in local democratic structures. Develop strategic relationships with key actors in the not-for-profit sector across Dublin City to further the goals of the PPN, and overall sector. |  |  |  |  |
| Action |  | Responsibility | Targets | Key Performance Indicators |
| 2.1 | Training for new Representatives and Secretariat An advisory committee to assist the current Representatives and Secretariat with their roles and functions on DCC committees. | Coordinator and Support Worker and consultant facilitator. “Retired” Secretariat and Representatives | New Representatives, Secretariat An advisory committee to meet on request to aid the Secretariat and staff. No formal decision-making powers, but able to offer advice/recommendations. | Ellenora Lynch, began her support sessions for the Pillar Working Groups in Q3 and completed these sessions in Q4. Ellenora’s final report is pending. The new advisory committee did not meet in person or online in Q4 but are connected via Whatsapp and the telephone. The aim of this advisory group, is to offer advice to new Representatives and Secretariat from a body of people, who have served on posts in the PPN. |
| 2.2 | Training and resources for the wider PPN | Coordinator and Support Worker. Coordinator and Support Worker. Support Worker and Coordinator. | The PPN and the Centre for Engaged Research (CER) at Dublin City University (DCU) will develop a PPN Summer School in 2025. The PPN will signpost training opportunities, and other supports, from already established training organisations, such as the Dublin City Volunteer Centre. The PPN will survey PPN member groups for training needs in early 2025. Member groups will be tracked during the year, which will lead to a report on participation levels within the PPN. Skills based online supports may be offered to PPN member groups (in partnership with DLR and Fingal PPNs), and further work on EDI and/or wellbeing may be considered if requested in the survey. | The PPN delivered a very successful summer school in the summer of 2025, and will host another summer school in 2026. The weekly Bulletin promoted the work of the Dublin City Volunteer Centre on social media, through the Bulletin and on the website in Q4. A pilot scheme will be launched in 2026, to assist PPN groups to work more with volunteers. (TBC). A successful series of general training sessions were delivered in Q4: “Grant Application Writing” with Evelyn Fitzgerald, “How to write successful submissions”, with Clare O’Connor and “How to care for others while caring for ourselves”, with Helena Dilleen. These sessions were offered in person during the daytime, and online, during the evening time. The sessions were offered in partnership with DLR PPN, and were offered free of charge. A short report on this series of training is pending. |
| Objective Three: Governance, Administration and Operating Procedures Goals: to support and empower Dublin City PPN to deliver upon its vision of being an effective and inspirational community representative network, through the establishment of robust operating procedures and demonstration of sectoral best practice. |  |  |  |  |
| Action |  | Responsibility | Targets | Key Performance Indicators |
| 3.1 | Fill any vacant seats in 2025 | Coordinator, Support Worker, and Neo-Archaic | There are no planned vacancies in 2025. | Two vacant seats were filled by the November Plenary and the final Secretariat seat was filled by the end of 2025 (to be ratified at the May 2026 Plenary). In 2026, there will be 2 LCDC seats, and 3 Secretariat seats available. |
| 3.2 | Coordinate plenaries in May 2025 and November 2025 | Coordinator and Support Worker | Hybrid plenaries will take place towards the end of May and November (depending on bank holidays). | The winter networking event (November Plenary) took place on 20 November in the Friends of the Elderly premises on Bolton Street, and was a great success. You can read the full summary of the event, here. |
| 3.3 | Attend PPN regional meetings | Coordinator, Support Worker and Secretariat | To meet colleagues in Dun Laoghaire Rathdown and Fingal PPN for support, skills sharing and planning. | The PPN staff of Dublin City and DunLaoghaire Rathdown met colleagues from DLR PPN for informal support and informal training in Q4. |
| 3.4 | The Secretariat of the PPN to meet to administer the work of the PPN | Coordinator and Support Worker | The Secretariat to meet monthly to discuss the ongoing work of the PPN, to govern, guide and discuss issues as they arise. | The Secretariat meets on the second Tuesday of the month every month except July, August and December and you can access the minutes here. |
| 3.5 | Documents required for the Department of Rural and Community Development | Coordinator, and Secretariat. Cordinator and Secretariat Coordinator, Support Worker and Secretariat | The 2024 Income and Expenditure Report to be completed by March 2025. The 2024 Annual Report to be completed by June 2025. The 2026 workplan and budget to be shared with the Plenary by November 2025. The PPN, the host (DCVC) and DCC should meet to discuss work, activities and ongoing budget reviews in 2025, once a quarter. The PPN policies and procedures documents to be reviewed and updated before the May 2025 plenary. The Implementation Roadmap (July 2024) document to be used as a guide to ensure policies and procedures are in line with good governance. The PPN Five Year Strategic Plan is to be reviewed and a new one developed. | The Income and Expenditure Report for 2024, was submitted in Q1 of 2025. Dublin City PPN submitted its annual report on 04 July. The report was co-signed by the PPN staff, the Secretariat and DCC, and submitted to Social Justice Ireland, who will collate all 31 PPN annual reports and deliver a national report by December 2025. There were no 3-way meetings in Q4, however, all three stakeholders communicate regularly via email/telephone conversations and face-to-face meetings. PPN staff attend the bi-weekly DCVC staff meetings. The Secretariat sub-group were unable to meet to review the policies and procedures documents, and so it was agreed that a consultant facilitator could be tasked with this job, as part of the delivery of a new PPN 5 Year Plan. This tender will be advertised in Q1 and the budget is allocated in the 2026 Budget, agreed at Plenary in November 2025. There were no updates in this area in Q4. There were no updates due in Q4. A tender for work on the next 5 Year Plan will take place in January 2026. In addition, a consultant facilitator will be tasked with developing further supports for the Pillar Working Groups. As agreed in Budget 2026. |
| 3.6 | Dublin City PPN to relate to national network frameworks and structures. | Coordinator and Support Worker and Secretariat. | Staff to meet PPN staff regionally and nationally, while one member of the PPN Secretariat to belong to the National Secretariat network and feedback to the Dublin City PPN secretariat. | All 31 PPNs’ staff meet online every quarter and provide daily/weekly support to one another on WhatsApp. The quarterly meetings are facilitated and noted by different staff. Mick Keegan, from the Dublin City PPN Secretariat, sits on the National Secretariat Networking group. The continuation of the National Housing SPC is unknown (to be updated by Mike Allen). The Environmental representatives meet through Catherine O’Toole and the IEN. Dublin City PPN sent six delegates to the National PPN Conference in Trim, in October 2025, and you can read a full summary of this activity here. |
| 3.7 | Maximise virtual technology to support the PPN as requested by Dublin City Council. Assist Dublin City Council staff as it organises events, consultations and information sessions. | All PPN stakeholders All PPN stakeholders | PPN members are better able to use technology to conduct PPN business. PPN to assist DCC’s launch of the LECP. PPN to share information about DCC’s work in the weekly Bulletin and through social media. PPN to attend Africa Day and host events to celebrate Inclusion and Integration Week. PPN to promote training sessions in libraries and at other venues. | PPN staff currently use: telephone/email/whatsapp/teams/zoom/Monday.com/sharepoint/salesforce/Slack/Basecamp/Facebook/LinkedIn and meets members in person. Most member groups prefer face-to-face meetings and staff aim to go on site visits every second week, to support member groups in their activities. The PPN were requested to work closer with DCC area offices, with organisations involving older people, and to provide additional supports to the LCDC. These additional requests were actioned in Q3. The ongoing mis/disinformation will take place in libraries in Q4, and discussions between area offices and the PPN continue (especially Finglas/Ballymun Whitehall/Clontarf and the D8/Liberties area of Dublin City, where PPN staff have made contact with the area managers. A mapping exercise is taking place, to match area offices, with the PPN Representatives, and this will conclude in Q4. |